## Slide 1
01
PORTFOLIO REVIEW · PROGRAMME BOARD
The portfolio, on one canvas.
Six initiatives over the next four quarters — how they're tracking, where they connect, and the few decisions that keep the whole programme moving.
HORIZON
6 active projects
HORIZON
Q3 2026 → Q2 2027
PORTFOLIO LEAD
A. Okafor
3 on track
2 watch
1 at risk
Notes: Frame the portfolio view: this is the whole programme on one canvas. The goal of this session is a holistic read on what's happening over the next few quarters, where the projects connect, and the few decisions that unblock the rest.

## Slide 2
PORTFOLIO · 02
Portfolio at a glance
On track
Watch
At risk
Data Platform
Lead L. Park · Foundational
Progress
78%
NEXT MILESTONE
Platform GA
12 Dec
Identity & SSO
Lead M. Díaz · Enabler
Progress
88%
NEXT MILESTONE
SSO GA
28 Nov
Payments Revamp
Lead S. Haddad · Revenue
Progress
45%
NEXT MILESTONE
Launch
27 Mar
Mobile App 2.0
Lead T. Bauer · Growth
Progress
22%
NEXT MILESTONE
Beta
20 Feb
Analytics Suite
Lead P. Novak · Insight
Progress
12%
NEXT MILESTONE
Analytics GA
15 May
Partner API
Lead R. Singh · Ecosystem
Progress
30%
NEXT MILESTONE
API v1
30 Apr
Horizon Portfolio · Programme Review | Confidential
02 / 10
Notes: One card per project — the whole portfolio in a single read. Scan the status dots first, then drop into the two ambers and the red. Each card carries the owner, progress, and the single next milestone that matters.

## Slide 3
ROADMAP · 03
Integrated roadmap & dependencies
Phase / progress
Milestone
Dependency
Today
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Data Platform
L. Park
Identity & SSO
M. Díaz
Payments Revamp
S. Haddad
Mobile App 2.0
T. Bauer
Analytics Suite
P. Novak
Partner API
R. Singh
TODAY
Platform GA
SSO GA
Launch
Beta
GA
Analytics GA
API v1
Horizon Portfolio · Programme Review | Confidential
03 / 10
Notes: The holistic view. Each lane is a project; diamonds are milestones; the dashed lines are the dependencies between projects. Trace the connections: SSO GA feeds Payments and Partner API; Platform GA feeds Analytics; Payments launch gates Mobile GA. The red line is today.

## Slide 4
DEPENDENCIES · 04
Where we depend on other teams
6
DEPENDENCIES
2
BLOCKED
3
DECISIONS DUE
Blocked
Pending
On track
Flag = decision due · dates show when each handoff is needed
15 Nov
Partner Team
Signed API contract · Partner API
Approve commercial terms · R. Singh
20 Nov
Security
Pen-test clearance · Identity & SSO
On track — no action needed
30 Nov
Legal
Partner DPA executed · Partner API
In review with Legal
02 Dec
Model Validation
Independent model sign-off · Risk Model v2
Book validation slot · A. Okafor
10 Jan
Data Governance
PII handling approval · Analytics Suite
Confirm data classification · P. Novak
05 Feb
Platform Ops
Prod environment ready · Mobile App 2.0
On track — no action needed
Horizon Portfolio · Programme Review | Confidential
04 / 10
Notes: This is the roadmap's external face: the handoffs we don't control. Two are blocked and need a decision this month — the model validation slot and the partner contract. Walk the flagged rows; each one names the call and who owns it. Greens are tracking and need no action today.

## Slide 5
MASTER TIMELINE · 05
Projects in parallel, dependencies flagged
Phase / progress
Milestone
Dependency (filled = decision due)
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Identity & SSO
M. Díaz
Partner API
R. Singh
Risk Model v2
S. Haddad
Analytics Suite
P. Novak
Mobile App 2.0
T. Bauer
TODAY
Security
20 Nov
Partner Team
15 Nov · decision
Legal
30 Nov
Model Validation
02 Dec · decision
Data Governance
10 Jan · decision
Platform Ops
05 Feb
Horizon Portfolio · Programme Review | Confidential
05 / 10
Notes: This is the master view: every project on its own lane, running in parallel, with the external-team dependencies flagged right where each one lands on the timeline. Filled flags are decisions due — Partner contract, model validation, data classification. Read down the Q4 column: three external calls converge in the same six weeks, which is the crunch.

## Slide 6
IMPACT · 06
A year of progress, measured
What Data Platform delivered over the last year — and the outcome it moved: analyst time on manual data prep.
ANALYST HRS / WEEK ON MANUAL PREP
▼ 56% YoY
14.0
11.5
9.0
7.4
6.2
NOW
Q3 '25
Q4 '25
Q1 '26
Q2 '26
Q3 '26
A YEAR AGO
14.0h/wk
TODAY
6.2h/wk
WHAT DROVE IT
Q4 '25
Automated ingestion pipeline
Q1 '26
Self-serve dataset catalog
Q2 '26
Reusable prep templates
Q3 '26
Inline validation autochecks
Horizon Portfolio · Programme Review | Confidential
06 / 10
Notes: Connect delivery to outcome. The metric is analyst hours per week on manual data prep. A year of Data Platform work took it from 14 hours to 6.2 — more than halved. The right column lists exactly what shipped to drive that down. Use this pattern for any project: pick the one metric the work moves, then show the trajectory.

## Slide 7
PLAN · 07
Planned enhancements & estimated effort
Where the next four quarters take the same metric — and what each step is estimated to cost.
PROJECTED HRS / WEEK
Projected
6.2
NOW
5.0
4.0
3.0
TARGET
Q3 '26
Q4 '26
Q1 '27
Q2 '27
ENHANCEMENT
EST. EFFORT
IMPACT
Smart anomaly checks
Q4 '26
6 eng-wks
−1.2 h/wk
Auto-reconciliation
Q1 '27
9 eng-wks
−1.0 h/wk
One-click reporting
Q2 '27
5 eng-wks
−1.0 h/wk
20 eng-weeks invested
→ target 3.0 h/wk (−52% from today)
Horizon Portfolio · Programme Review | Confidential
07 / 10
Notes: Now the forward look. Same metric, projected to 3.0 hours by Q2 next year. The right column is the plan: each enhancement with its estimated effort in engineering-weeks and the time it's expected to save. The bottom line ties it together — 20 eng-weeks of investment buys another halving of analyst time.

## Slide 8
IMPACT · 08
Impact over time — one view
Analyst hours / week on manual prep: a year delivered, a year planned, and the effort between.
Delivered
Projected
14.0
11.5
9.0
7.4
6.2
NOW
5.0
4.0
3.0
TARGET
Q3 '25
Q4 '25
Q1 '26
Q2 '26
Q3 '26
Q4 '26
Q1 '27
Q2 '27
A YEAR AGO
14.0
TODAY
6.2
TARGET '27
3.0
DELIVERED
−7.8 h/wk
Q4 '25
Automated ingestion pipeline
Q1 '26
Self-serve dataset catalog
Q2 '26
Reusable prep templates
Q3 '26
Inline validation autochecks
PLANNED NEXT
20 eng-weeks
Smart anomaly checks
Q4 '26 · 6 eng-wks
−1.2
Auto-reconciliation
Q1 '27 · 9 eng-wks
−1.0
One-click reporting
Q2 '27 · 5 eng-wks
−1.0
Horizon Portfolio · Programme Review | Confidential
08 / 10
Notes: The same impact story on one slide: solid bars are delivered, dashed bars are projected, the line splits past from forecast. A year of work halved the metric to 6.2; another 20 engineering-weeks is forecast to halve it again to 3.0. Use this single-slide version when you want the whole arc in one view instead of two.

## Slide 9
DEEP DIVE · 09
Smart anomaly checks
Auto-flag statistical anomalies in prepped data before analysis — the next manual step to remove.
Planned · Q4 2026
BACKGROUND
Analysts still eyeball each dataset for outliers before sign-off — slow, ad-hoc, and inconsistent between people. Now that data prep is automated, manual anomaly hunting is the largest remaining hand step in the workflow.
GOAL
Surface the anomalies automatically, with an explainable reason for each — so the analyst reviews and decides, instead of searching.
IN SCOPE
●
Statistical baselines per dataset
●
Inline severity flags in the catalog
●
One-click accept / dismiss + audit trail
○
Out of scope: auto-correction
OWNER
P. Novak
TEAM
1 DS · 1 Eng
TIMELINE
14 Oct → 28 Nov
EFFORT
6 eng-weeks
DEPENDS ON
Prep templates ✓
ESTIMATED BENEFIT
−1.2
analyst hrs / week per person
~1,500
hrs / year returned
< 1 qtr
effort payback
Horizon Portfolio · Programme Review | Confidential
09 / 10
Notes: A one-pager template for introducing a single piece of work in depth. Use it when a project or enhancement needs its own moment: the background and why-now on the left, the facts and the benefit case on the right. Here it profiles Smart anomaly checks — owner, effort, timeline, and the estimated hours returned.

## Slide 10
CONNECTIONS & DECISIONS · 10
SSO GA is the long pole.
Three initiatives gate on it. Slip the 28 Nov date and the whole right-hand side of the roadmap moves with it.
SSO GA
→
Payments Revamp · Partner API · Mobile App 2.0
Platform GA
→
Analytics Suite
Payments Launch
→
Mobile App 2.0 GA
DECISIONS WE NEED TODAY
1
Protect the SSO GA date
Freeze scope on Identity; add one engineer from Analytics.
2
Resequence Partner API behind SSO
Move API v1 to early Q2 to clear the red status.
3
Confirm Analytics start gated on Platform GA
Hold kickoff to 12 Dec; no early ramp.
Next portfolio review: Programme Board · 18 Dec 2026
Horizon Portfolio · 10 / 10
Notes: Turn the connections into decisions. SSO GA is the long pole — three projects sit behind it, so protecting that date is the single highest-leverage call. Then two sequencing decisions follow. Confirm all three before we close.